## Sheet1
Risk / Concern | Impact | Likelihood | Current Status | Last Updated | Notes
Interconnectivity of seperate areas of code worked on | 4 | 6.5 | We have had issues in the beginning of several team members working on the same portion of code, not using our time worked on this project efficiently. We have resolved this by being more dilligent with our updates to GitHub and emphasizing communication |  | Solved with GIt Hub
Connecting HTML to the Database | 10 | 3.5 | There were issues early in the project of not being able to connect, but this was solved through searching through YouTube videos
Visual Appearance of Website | 3 | 5.5 | First version of this site was not appeasing to the eye, Lydia worked on updates to this portion to make the website look more professional
Log-In Issues | 6 | 1.5 | Log-In Page was one of the easier pages for us to program as this is a staple in most websites |  | Forgot password added, along with the ability to join as a guest
Shopping Cart Issue | 7 | 6 | For the shopping cart, updates currently show and are saved on the website, but updates do not always reflect what is showing in the database. This is an issue that is central to company inventory and would require immediate attention for a real company
Shoe Inventory Issues | 5 | 5 | Bryan worked on the Database portion of the code which stores this information, but as mentioned with the shopping cart, updates from website need to be saved here and are not currently
Billing Information Issues | 7 | 3.5 | Several of the issues surrounding Billing information include the need for the security of this data, a need to validate this information with the banks, and a way to ensure all of the proper data types are being used in the correct sections |  | Would most likely be solved by using a third party app such as Stripe that could serve to valudate this information
Database Updates | 10 | 4.5 | Along with inventories, the need to store user data is also a big part of this database, and securities would be needed in order to keep this information confidential. Access exceptions would be needed to be granted to different types of users
Time Management | 4.5 | 8.5 | With this group working on two projects together, while also taking classes and participating in sports, time constraints are a legitimate issue for our team. Detailed and early planning was necessary in order to make meetings come to fruition
Software Skill Level | 3.5 | 4.5 | One of the most common issues we have encountered is purely the lack of knowledge or comfortability with some concepts, so it was necessary for our team to factor in the amount of time it would take to complete various tasks